## Slide 1: Scrum and VS 2010
Simon Reindl
Accentient
simon@accentient.com

## Slide 2: Agenda
Scrumdamentals
  Context - Agile
  Overview
  Roles
  Time Boxes
  Artefacts
  Rules
Scrum with VS2010
  Hints
  Best Practices
  Templates

## Slide 3: Agile on one slide
Waterfall
Comprehensive process
Formal complete specification
Full Design
BDUF
Coding
Testing
Stabilisation
Release
Agile
Lighter framework
Short iteration
Many techniques
  XP
  TDD
  CI
  Etc.

## Slide 4: What kind of problem?
http://www.lostgarden.com/2006/04/managing-game-design-risk-part-i.html

## Slide 5: The Agile Manifesto
Individuals and interactions over processes and tools
Working software over comprehensive documentation
Customer collaboration over contract negotiation
Responding to change over following a plan
http://agilemanifesto.org/

## Slide 6: Scrum @ 60,000 feet
Scrum is the most popular of the agile development frameworks
Iterative and empirical approach to solve complex problems
Each sprint the focus is to build an increment of potentially shippable functionality
Can utilise other processes or techniques within the framework

## Slide 7: Scrum @ 30,000 feet
Iterative, incremental approach to reduce risk and maintain focus on goals
Regular “inspect and adapt” reviews of the product, as well as the team
Transparency key to achieving success
Cross-functional, self managing teams (7 ± 2 members)

## Slide 8: Scrum @ 10,000 feet
Roles | Timeboxes | Artefacts
Product Owner | Release Planning Meeting | Product Backlog
ScrumMaster | Sprint Planning Meeting | Sprint Backlog
The Team | The Sprint | Burndown Chart
 | Daily Scrum Meeting | Working Software
 | Sprint Review Meeting | 
 | Sprint Retrospective | 

## Slide 9: The pig and the chicken

## Slide 10: The Pigs
The Scrum Team
Team
Scrum Master
Product Owner

## Slide 11: The Chickens
Anyone else!
Other Scrum Teams
The Customer
The Sales Team
The Chief executive
The Cleaner

## Slide 12: Product Owner
Voice of the customer
Defines the “What” of the product
Manages business value
Owns Product Backlog
Can change priorities of the product backlog – but not after it has been taken in to the sprint

## Slide 13: Scrum Master
Manages the process
Shields team and removes impediments
Ensures team is cross-functional and focussed on improving quality
Facilitates close working between the Product Owner and The Team
Facilitator and a coach

## Slide 14: The Team
Commit to create product backlog items into increments of potentially shippable functionality every sprint
Responsible for the “how”
Need to be cross-functional
No Titles, No Silos
Co-operative culture
Self Organising

## Slide 15: Scrum Framework
Product
Backlog
Task
Task
Task
Sprint
Backlog
Sprint
2 – 4
Weeks
24
Hours
Product

## Slide 16: Its all about timing!
No Peaks and troughs
8 hour burn
Sustainable pace
No “Death Marches”

## Slide 17: Time Boxes
Release Planning Meeting
Sprint Planning Meeting
The Sprint
Daily Scrum Meeting
Sprint Review Meeting
Sprint Retrospective

## Slide 18: Start up meetings
Release Planning Meeting
  Overall plan on how to realise the vision
  What is going to be in the first sprint(s)
  Based upon the prioritised Product Backlog (list of items – PBI)
Sprint Planning Meeting
  The team commits to achieving a Sprint Goal
  Team creates the Sprint Backlog
  Tasks needed to fulfil the selected PBI
  Is the start of the sprint

## Slide 19: DoD = Definition of Done
Agreed between Product Owner and the Team
Same across the enterprise
Start small and grow
Not done items not demonstrated at the review
Critical for the Team to keep this in sight

## Slide 20: What is Done?
Fundamental
Mature
Code Analysis
Coded
Refactored
Code Reviewed
Unit Tested
Documented
Continuous Build
User Acceptance
Design Review
Design Refactored
Integration Tested
Regression Tested
Security Tested
Load/Soak Tested
Scalability Tested
Performance Tested

## Slide 21: The Sprint (aka Iteration)
The time that the team builds an increment of potentially shippable functionality
As short as possible and no shorter (2-4 weeks)
Strict time box
Has a Daily Scrum Meeting
Start with Sprint Planning Meeting
End with Sprint Review Meeting and Sprint Retrospective Meeting

## Slide 22: Daily Scrum Meeting
15 minute stand up
3 questions
  What have you done since the last Scrum?
  What will you do between now and the next Scrum?
  What is in your way?
Not a status meeting
Not a problem solving meeting
  Take it offline!

## Slide 23: Development
The Team focuses on achieving the sprint goal
Self manages on how to achieve
Work delivered to the standard agreed in the definition of Done
Minimal interruptions
No change in sprint stories for the duration of the sprint

## Slide 24: Sprint Review Meeting
Review Sprint Goal and Committed Product Backlog Items
The Team Presents the work “done”
  Undone work is not shown
Informal
All Welcome (chickens, pigs, et al)
Time Boxed!
Hint – use a demo script

## Slide 25: Sprint Retrospective Meeting
Team participates
  No chickens
What was achieved?
What went well?
What could be improved on?
Review Metrics
Tasks for next sprint
Everyone should contribute

## Slide 26: Artefacts
The Product Backlog
The Sprint Backlog
Burndown Charts

## Slide 27: The Product Backlog
Owned by the Product Owner
Anyone can add to it
Regularly groomed by the Scrum Team
Each PBI has business value
High level estimates
  Planning Poker
  Size Only

## Slide 28: The PBI Iceberg
Detail
And
Understanding
Increase
towards
the top
The top
items have
The highest
Business
priority

## Slide 29: Sprint Backlog
Tasks needed to complete Sprint Goal
Most created in Sprint Planning
Tasks emerge throughout Sprint
Task no more than 1 Day
  Team estimate
  Can use planning poker

## Slide 30: Burndown Chart
Work Remaining over Time

## Slide 31: Traps And Dysfunctions
Start small
Don’t change Scrum
  Highlights the issues
  Issue existed before Scrum
No Product Owner
ScrumMaster is the Product Owner
Need Management Commitment for it to stick

## Slide 32: Engineering Practices
Principles
  Coupling, Cohesion, testability
Patterns
  MS patterns & Practices, Gang of 4
Practices
  TDD, Design by Contract, Defensive Programming
  SOLID
Notes: Initial
Stands for (acronym)
Concept
S
SRP
Single responsibility principle the notion that an object should have only a single responsibility.
O
OCP
Open/closed principle the notion that “software … should be open for extension, but closed for modification”.
L
LSP
Liskov substitution principle see also design by contract.
I
ISP
Interface segregation principle the notion that “many client specific interfaces are better than one general purpose interface.”[5]
D
DIP
Dependency inversion principle the notion that one should “Depend upon Abstractions. Do not depend upon concretions.”[5] Dependency injection is one method of following this principle.

## Slide 33: How VS2010 Helps
Modelling (ultimate)
Test-First Development
Refactoring
Unit / System Testing
Continuous Integration
Code Analysis
Automated Testing
  Coded UI Tests
Intellitrace
Wix 3.5 Support
Database Projects

## Slide 34: Process Templates
Microsoft Scrum
  http://visualstudiogallery.msdn.microsoft.com/en-us/59ac03e3-df99-4776-be39-1917cbfc5d8e
MSF Agile
  Comes in the box!
Conchango V3
  http://scrumforteamsystem.com/

## Slide 35: Hints
Get a build server running
Use CI
What is the Branching Strategy
Set up XML Documentation
Use Code Analysis
Unit Test (at Least) early and often
Get the deployment sorted early
Use models to understand and refactor

## Slide 36: Demo
Modelling Tools
Backlogs
Work Items

## Slide 37: Professional Scrum Developer
New Program Just Launched in collaboration with
  Microsoft
  Scrum.org (founded by Ken Schwaber)
5 days training aimed at the development team and teaching how to develop a potentially shipable increment using
  Scrum
  Visual Studio 2010
  Modern Engineering
Dates 13-17 September Microsoft TVP Reading

## Slide 38: To book your place
http://courses.scrum.org/classes/show/66
http://www.accentient.com/scrum
Email: simon@accentient.com
Early booking and group discount available. Email for options.

## Slide 39: Questions

## Slide 40: Links
http://www.scrum.org
http://www.accentient.com/scrum
http://msdn.microsoft.com/en-us/vstudio/ff433643.aspx

## Slide 41: Thank You
Contact:
Twitter s_reindl
Twitter Tag #proscrumdev
Email simon@accentient.com
Blog: http://blog.accentient.com/